## Overview
Manual 3-RPS Rev M1 ¦ Final BOM and CAD Verification
Manual leveling/lifting module only. Powered actuators, batteries, controllers, sensors, diodes and fuses are excluded. Adjustment requires an independently supported, unloaded upper frame.
Budget cap (KRW) | 4000000 |  | Native CAD components | 129
Known-price subtotal | 320845 |  | BOM rows | 28
Budgetary total | 2257845 |  | Fusion interference | PASS (0 / 0 / 0)
Remaining to cap | 1742155 |  | Fusion sections | 3 PASS
Quote/option rows | 13 |  | Independent STEP | PASS
Order release | HOLD - QUOTES REQUIRED |  | BOM-CAD passes | PASS (3 + repeat)
Design status | DETAILED REVIEW COMPLETE; ORDER HOLD |  | CAD coverage | 129/129
Order-release hold points
1 | BJ775-08040-SUS | Exact code, 40 mm grip and delivered Korean quote | OPEN
2 | OD32/OD25 tube stock | Receive and measure before final JFM housing/shaft machining | OPEN
3 | Pivot pin sets | Supplier drawings must keep all threads outside bearing surfaces | OPEN
4 | DIN439 M10 thin nuts | 17 AF x 5 mm exact envelope; no DIN936 substitution | OPEN
5 | A1 trial build | Dry-build one support before releasing the remaining custom sets | OPEN

## BOM
Manual 3-RPS Rev M1 ¦ Procurement BOM
Known unit prices are recorded separately from budget allowances. Budget allowance is not a supplier quote. Use Status and Preorder condition before adding an item to a cart.
Line | Group | Category | Item | Exact specification | Supplier | Supplier code | Used qty | Order qty | Order unit | Known unit KRW | Budget unit KRW | Known extended | Budget extended | Status | Preorder condition | Product URL | Price basis | Dimension basis
S01 | NAVI | Lower frame | DNF4040 aluminum profile, 700 mm | 40 x 40, 700 mm cut, slot 8.3 +/-0.3, center bore 6.8/M8 family | NAVIMRO | K92787708 | 2 | 2 | EA | 21989 | 21989 | 43978 | 43978 | READY_TO_CART | Confirm straight cut and no end tapping | https://www.navimro.com/p/K92787708/ | 2026-09-01 VAT-included screen price | NAVIMRO DNF4040 detail image; received profile to be checked before machining
S02 | NAVI | Lower frame | DNF4040 aluminum profile, 620 mm | 40 x 40, 620 mm cut, slot 8.3 +/-0.3, center bore 6.8/M8 family | NAVIMRO | K92787705 | 4 | 4 | EA | 19789 | 19789 | 79156 | 79156 | READY_TO_CART | Order-made/nonreturnable; reconfirm 620 mm cut | https://www.navimro.com/p/K92787705/ | 2026-09-01 VAT-included screen price | NAVIMRO DNF4040 detail image
S03 | NAVI | Upper frame | DNF3030-6 aluminum profile, 700 mm | 30 x 30, 700 mm cut, slot 6.3 +0.2/0, center bore 6 | NAVIMRO | K42296106 | 2 | 2 | EA | 7689 | 7689 | 15378 | 15378 | READY_TO_CART | Confirm collect freight and 700 mm cut | https://www.navimro.com/p/K42296106/ | 2026-09-01 VAT-included screen price | NAVIMRO DNF3030 detail image
S04 | NAVI | Upper frame | DNF3030-6 aluminum profile, 640 mm | 30 x 30, 640 mm cut, slot 6.3 +0.2/0, center bore 6 | NAVIMRO | K42296071 | 4 | 4 | EA | 6589 | 6589 | 26356 | 26356 | READY_TO_CART | Confirm collect freight and 640 mm cut | https://www.navimro.com/p/K42296071/ | 2026-09-01 VAT-included screen price | NAVIMRO DNF3030 detail image
S05 | NAVI | Profile bracket | 4035 right-angle bracket | 40 x 40 x 35, nominal t6, two 9 x 18 slots | NAVIMRO | K92782553 | 8 | 8 | EA | 913 | 913 | 7304 | 7304 | READY_TO_CART | Bolts and slot nuts ordered separately | https://www.navimro.com/p/K92782553/ | 2026-09-01 VAT-included screen price | NAVIMRO 4035 detail images
S06 | NAVI | Profile bracket | DCB3025 right-angle bracket | 30 x 30 x 25, two diameter-7 mounting holes | NAVIMRO | K56842696 | 8 | 8 | EA | 660 | 660 | 5280 | 5280 | READY_TO_CART | Bolts and slot nuts ordered separately | https://www.navimro.com/p/K56842696/ | 2026-09-01 VAT-included screen price | NAVIMRO DCB3025 detail images
C01 | MACHINE | Custom adapter | Lower local adapter | 120 x 80 x 8; two diameter-9 through holes at 96 pitch; two M8 x 1.25 tapped holes at 40 pitch | Machining quote | M1-C01 | 3 | 3 | EA |  | 30000 |  | 90000 | READY_TO_QUOTE | Tap after diameter-6.8 drilling; deburr all edges | https://www.skb-steel.com/product/detail.html?product_no=235 | Budget allowance only; drawing quotation required | Fusion Rev M1 native CAD and custom-part dimension table
C02 | MACHINE | Custom clevis | Lower one-piece clevis | Base 60 x 50 x 8; clear gap 34; ears t6; outside width 46; pivot diameter 8.2; pivot center 28 above base top | Machining quote | M1-C02 | 3 | 3 | EA |  | 120000 |  | 360000 | READY_TO_QUOTE | Machine from one billet; no welding; maintain coaxial pivot bores | https://www.skb-steel.com/product/detail.html?product_no=235 | Budget allowance only; 3-axis machining quotation required | Fusion Rev M1 native CAD
C03 | MACHINE | Custom clevis | Upper one-piece clevis | Base 100 x 60 x 8; mounting pitch 84; clear gap 20; ears t6; outside width 32; pivot diameter 10.2 | Machining quote | M1-C03 | 3 | 3 | EA |  | 120000 |  | 360000 | READY_TO_QUOTE | Machine from one billet; no welding; maintain coaxial pivot bores | https://www.skb-steel.com/product/detail.html?product_no=235 | Budget allowance only; 3-axis machining quotation required | Fusion Rev M1 native CAD and THK PHS10 envelope
C04 | MACHINE | Manual strut | Finished outer tube | OD32 x ID28 x L160; upper 21 mm housing reamed to diameter 28.000-28.021; lower pivot bore diameter8.2; coarse-pin bore diameter8 +0.1/0 | Tube stock plus machining quote | M1-C04 | 3 | 4 | EA |  | 50000 |  | 200000 | READY_TO_QUOTE | Machine bushing housing after tube receipt; inspect ID before reaming |  | Budget allowance; stock and machining quotation required | Fusion Rev M1 CAD plus igus JFM housing tolerance
C05 | MACHINE | Manual strut | Finished inner tube | OD25 shaft tolerance 24.948-25.000 x ID21 x L150; six diameter8 +0.1/0 coarse holes at 15 pitch; one diameter-4.2 retainer hole | Tube stock plus machining quote | M1-C05 | 3 | 4 | EA |  | 35000 |  | 140000 | READY_TO_QUOTE | Verify actual OD is within 24.948-25.000 before ordering batch machining |  | Budget allowance; stock and machining quotation required | Fusion Rev M1 CAD plus igus JFM shaft tolerance
C06 | MACHINE | Manual strut | Lower guide ring | OD27.6 x ID25.10 x L12, split installation permitted | Machining quote | M1-C06 | 3 | 4 | EA |  | 15000 |  | 60000 | READY_TO_QUOTE | Deburr and dry-fit with actual inner/outer tubes |  | Budget allowance only | Fusion Rev M1 native CAD
C07 | MACHINE | Manual strut | M10 threaded insert plug | OD20.8 x L30; axial M10 x 1.5 thread depth 22 minimum; diameter-4.2 retainer cross hole 7.5 from plug lower end (22.5 from outer end) | Turning quote | M1-C07 | 3 | 4 | EA |  | 25000 |  | 100000 | READY_TO_QUOTE | Cross drill plug and inner tube together after dry fit |  | Budget allowance only | Fusion Rev M1 native CAD
M01 | BEARING | Bushing | igus JFM-2528-21 flanged sleeve bearing | ID25, OD28, flange OD35, L21, flange t1.5 | DeviceMart | 10896543 / JFM-2528-21 | 3 | 4 | EA | 1870 | 1870 | 7480 | 7480 | READY_TO_CART_AFTER_STOCK_CHECK | Confirm four pieces and current lead time | https://www.devicemart.co.kr/goods/view?no=10896543 | VAT-included product page price; page stated average lead time two weeks | igus JFM catalog and product detail image
M02 | BEARING | Rod end | THK PHS10 RH female rod end | Bore 10 H7, OD26, ring width14, overall56, center-to-thread-end43, M10 x 1.5, thread depth21, static radial 13.2 kN | SL System | PHS10 | 3 | 4 | EA | 13290 | 13290 | 53160 | 53160 | READY_TO_CART_AFTER_MODEL_CHECK | Order right-hand PHS10 only; do not substitute PHS10L or PHS6 | https://myslmall.com/category/PHS/146/ | Current indexed product page price | THK official PHS catalog; not inferred from seller thumbnail
M03 | IMPORT | Coarse lock pin | IMAO BJ775-08040-SUS ball-lock ring pin | Shank diameter8, maximum envelope9.4, grip L40 +0.5/0, end allowance8 +/-1, mass42 g | IMAO/MISUMI import quotation | BJ775-08040-SUS | 3 | 3 | EA |  | 100000 |  | 300000 | SUPPLIER_QUOTE_REQUIRED | Do not substitute another grip length; supplier must confirm exact code | https://www.imao.com/catalog/en/categoryviews/?category=%24900337&categorycode=%24WHSSAP%2C%24whs&page=1 | Budget allowance; Korean delivered quote required | IMAO official BJ775-SUS PDF and official CAD listing
F01 | NAVI | Frame fastener | M8 x 16 socket cap screw | SCM435 class 10.9, full thread, pack 36 | NAVIMRO | K53536280 | 22 | 1 | PK_36 | 7579 | 7579 | 7579 | 7579 | READY_TO_CART | 16 for 4035 brackets and 6 for lower clevises | https://www.navimro.com/p/K53536280/ | 2026-09-01 VAT-included screen price | Fusion positioned fastener components
F02 | NAVI | Frame fastener | M8 x 20 socket cap screw | SCM435 class 10.9, full thread, pack 34 | NAVIMRO | K53536553 | 6 | 1 | PK_34 | 7359 | 7359 | 7359 | 7359 | READY_TO_CART | For three lower adapters, two each | https://www.navimro.com/p/K53536553/ | 2026-09-01 VAT-included screen price | Fusion positioned fastener components
F03 | NAVI | Frame fastener | M6 x 15 socket cap screw | SCM435 class 10.9, full thread, pack 57 | NAVIMRO | K53536246 | 22 | 1 | PK_57 | 6039 | 6039 | 6039 | 6039 | READY_TO_CART | 16 for DCB3025 brackets and 6 for upper clevises | https://www.navimro.com/p/K53536246/ | 2026-09-01 VAT-included screen price | Fusion positioned fastener components
F04 | NAVI | Profile nut | SP408 M8 spring slot nut | 40-series M8 slot nut, pack 100 | NAVIMRO | K14671419 | 22 | 1 | PK_100 | 25289 | 25289 | 25289 | 25289 | READY_TO_CART | Used with F01 bracket bolts and F02 adapter bolts | https://www.navimro.com/p/K14671419/ | 2026-09-01 VAT-included screen price | NAVIMRO spring-nut detail image
F05 | NAVI | Profile nut | SP306 M6 spring slot nut | 30-series M6 slot nut, pack 100 | NAVIMRO | K14671215 | 22 | 1 | PK_100 | 25289 | 25289 | 25289 | 25289 | READY_TO_CART | Used with F03 bolts | https://www.navimro.com/p/K14671215/ | 2026-09-01 VAT-included screen price | NAVIMRO spring-nut detail image
F06 | NAVI | Fine adjuster | M10 x 1.5 threaded rod, 285 mm | Fully threaded; cut three pieces to L53 and deburr | NAVIMRO | K54170031 | 3 | 1 | EA_285MM | 1309 | 1309 | 1309 | 1309 | READY_TO_CART_AND_CUT | Cut only after confirming PHS10 right-hand thread | https://www.navimro.com/p/K54170031/ | 2026-09-01 VAT-included screen price | Fusion M10 x 1.5 stud components
F07 | SPECIAL | Fine adjuster | DIN 439 M10 thin jam nut | M10 x 1.5, across flats 17, thickness 5, right-hand thread | MISUMI/KIPP equivalent quote | DIN439-M10-17x5 | 6 | 10 | EA |  | 1500 |  | 15000 | EXACT_SIZE_QUOTE_REQUIRED | Supplier drawing must show 17 mm AF and 5 mm thickness |  | Budget allowance; exact dimensional quote required | Fusion thin-nut envelope; do not replace with 16 x 6 DIN936 without CAD revision
F08 | MACHINE | Pivot hardware | Lower shoulder pin and prevailing-torque locknut set | Shoulder diameter 7.98 h9, grip 46, head diameter14 x 7; M8 threaded end and 13 AF x 6.5 locknut | Configured shoulder bolt or turning quote | M1-F08 | 3 | 4 | SET |  | 30000 |  | 120000 | READY_TO_QUOTE | No thread may lie inside either clevis ear or outer tube pivot bore |  | Budget allowance; supplier drawing required | Fusion lower clevis outside grip 46
F09 | MACHINE | Pivot hardware | Upper shoulder pin and prevailing-torque locknut set | Shoulder diameter 9.98 h9, grip 32, head diameter16 x 5; M10 threaded end and 17 AF x 8 locknut | Configured shoulder bolt or turning quote | M1-F09 | 3 | 4 | SET |  | 35000 |  | 140000 | READY_TO_QUOTE | No thread may lie inside clevis ears, shims, or PHS10 bore |  | Budget allowance; supplier drawing required | Fusion upper clevis outside grip 32 and PHS10 bore 10 H7
F10 | MACHINE | Pivot hardware | Upper side shim | ID10.2, OD18, thickness3 | Laser/turning quote or exact shim supplier | M1-F10 | 6 | 8 | EA |  | 5000 |  | 40000 | READY_TO_QUOTE | Thickness tolerance +/-0.05 preferred; verify free articulation after assembly |  | Budget allowance only | 20 mm clevis gap minus 14 mm PHS ring width
F11 | NAVI | Retainer hardware | M4 x 40 socket cap screw plus M4 nyloc nut | Under-head length 40, modeled installed grip 32; low-load insert retention only | NAVIMRO option selection | SELECT-M4x40-AND-M4-NYLOC | 3 | 4 | SET |  | 3000 |  | 12000 | OPTION_SELECTION_REQUIRED | Use nylon-insert nut; do not apply high clamp load to the aluminum tube | https://www.navimro.com/ | Budget allowance; exact option to be selected at checkout | Fusion retainer component, inner tube OD25 and modeled 32 mm grip
F12 | NAVI | Consumable | LOCTITE 243 medium-strength threadlocker | 10 ml | NAVIMRO | K64647607 | 1 | 1 | EA | 9889 | 9889 | 9889 | 9889 | READY_TO_CART | Do not lock either fine-adjuster jam-nut interface before final setting | https://www.navimro.com/p/K64647607/ | 2026-09-01 VAT-included screen price | Assembly process consumable; intentionally not represented as CAD component

## CAD Mapping
BOM to Native Fusion Component Mapping
Each BOM row is matched to the 129 native Fusion leaf-component names. Proxy rows share a positioned fastener component because one Fusion component contains both bolt and slot-nut bodies.
Line | Item | CAD regex pattern(s) | Physical used | Expected CAD | Factor | Proxy | Pass 1 | Pass 2 | Pass 3 | Result | Matched component names
S01 | DNF4040 aluminum profile, 700 mm | ^LOWER_SIDE_[LR]_DNF4040_700$ | 2 | 2 | 1 | NO | 2 | 2 | 2 | PASS | LOWER_SIDE_L_DNF4040_700; LOWER_SIDE_R_DNF4040_700
S02 | DNF4040 aluminum profile, 620 mm | ^LOWER_CROSS_.*_DNF4040_620$ | 4 | 4 | 1 | NO | 4 | 4 | 4 | PASS | LOWER_CROSS_A1_DNF4040_620; LOWER_CROSS_A23_DNF4040_620; LOWER_CROSS_FRONT_DNF4040_620; LOWER_CROSS_REAR_DNF4040_620
S03 | DNF3030-6 aluminum profile, 700 mm | ^UPPER_SIDE_[LR]_DNF3030_700$ | 2 | 2 | 1 | NO | 2 | 2 | 2 | PASS | UPPER_SIDE_L_DNF3030_700; UPPER_SIDE_R_DNF3030_700
S04 | DNF3030-6 aluminum profile, 640 mm | ^UPPER_CROSS_.*_DNF3030_640$ | 4 | 4 | 1 | NO | 4 | 4 | 4 | PASS | UPPER_CROSS_A1_DNF3030_640; UPPER_CROSS_A23_DNF3030_640; UPPER_CROSS_FRONT_DNF3030_640; UPPER_CROSS_REAR_DNF3030_640
S05 | 4035 right-angle bracket | ^BRACKET4035_[1-4]_[LR]$ | 8 | 8 | 1 | NO | 8 | 8 | 8 | PASS | BRACKET4035_1_L; BRACKET4035_1_R; BRACKET4035_2_L; BRACKET4035_2_R; BRACKET4035_3_L; BRACKET4035_3_R; BRACKET4035_4_L; BRACKET4035_4_R
S06 | DCB3025 right-angle bracket | ^DCB3025_[1-4]_[LR]$ | 8 | 8 | 1 | NO | 8 | 8 | 8 | PASS | DCB3025_1_L; DCB3025_1_R; DCB3025_2_L; DCB3025_2_R; DCB3025_3_L; DCB3025_3_R; DCB3025_4_L; DCB3025_4_R
C01 | Lower local adapter | ^A[1-3]_LOWER_ADAPTER_A6061_120x80x8$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_LOWER_ADAPTER_A6061_120x80x8; A2_LOWER_ADAPTER_A6061_120x80x8; A3_LOWER_ADAPTER_A6061_120x80x8
C02 | Lower one-piece clevis | ^A[1-3]_LOWER_ONE_PIECE_CLEVIS_A6061$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_LOWER_ONE_PIECE_CLEVIS_A6061; A2_LOWER_ONE_PIECE_CLEVIS_A6061; A3_LOWER_ONE_PIECE_CLEVIS_A6061
C03 | Upper one-piece clevis | ^A[1-3]_UPPER_ONE_PIECE_CLEVIS_A6061$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_UPPER_ONE_PIECE_CLEVIS_A6061; A2_UPPER_ONE_PIECE_CLEVIS_A6061; A3_UPPER_ONE_PIECE_CLEVIS_A6061
C04 | Finished outer tube | ^A[1-3]_OUTER_TUBE_OD32x2_L160_REAM28H7$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_OUTER_TUBE_OD32x2_L160_REAM28H7; A2_OUTER_TUBE_OD32x2_L160_REAM28H7; A3_OUTER_TUBE_OD32x2_L160_REAM28H7
C05 | Finished inner tube | ^A[1-3]_INNER_TUBE_OD25x2_L150_6POS$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_INNER_TUBE_OD25x2_L150_6POS; A2_INNER_TUBE_OD25x2_L150_6POS; A3_INNER_TUBE_OD25x2_L150_6POS
C06 | Lower guide ring | ^A[1-3]_POM_LOWER_GUIDE_RING$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_POM_LOWER_GUIDE_RING; A2_POM_LOWER_GUIDE_RING; A3_POM_LOWER_GUIDE_RING
C07 | M10 threaded insert plug | ^A[1-3]_A6061_M10_THREADED_PLUG$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_A6061_M10_THREADED_PLUG; A2_A6061_M10_THREADED_PLUG; A3_A6061_M10_THREADED_PLUG
M01 | igus JFM-2528-21 flanged sleeve bearing | ^A[1-3]_IGUS_JFM_2528_21$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_IGUS_JFM_2528_21; A2_IGUS_JFM_2528_21; A3_IGUS_JFM_2528_21
M02 | THK PHS10 RH female rod end | ^A[1-3]_THK_PHS10_RH$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_THK_PHS10_RH; A2_THK_PHS10_RH; A3_THK_PHS10_RH
M03 | IMAO BJ775-08040-SUS ball-lock ring pin | ^A[1-3]_IMAO_BJ775_08040_SUS_COARSE_PIN$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_IMAO_BJ775_08040_SUS_COARSE_PIN; A2_IMAO_BJ775_08040_SUS_COARSE_PIN; A3_IMAO_BJ775_08040_SUS_COARSE_PIN
F01 | M8 x 16 socket cap screw | ^BRACKET4035_[1-4]_[LR]_BOLT_[XY]$ ¦ ^A[1-3]_CLEVIS_TO_ADAPTER_M8x16_[12]$ | 22 | 22 | 1 | NO | 22 | 22 | 22 | PASS | A1_CLEVIS_TO_ADAPTER_M8x16_1; A1_CLEVIS_TO_ADAPTER_M8x16_2; A2_CLEVIS_TO_ADAPTER_M8x16_1; A2_CLEVIS_TO_ADAPTER_M8x16_2; A3_CLEVIS_TO_ADAPTER_M8x16_1; A3_CLEVIS_TO_ADAPTER_M8x16_2; BRACKET4035_1_L_BOLT_X; BRACKET4035_1_L_BOLT_Y; BRACKET4035_1_R_BOLT_X; BRACKET4035_1_R_BOLT_Y; BRACKET4035_2_L_BOLT_X; BRACKET4035_2_L_BOLT_Y; BRACKET4035_2_R_BOLT_X; BRACKET4035_2_R_BOLT_Y; BRACKET4035_3_L_BOLT_X; BRACKET4035_3_L_BOLT_Y; BRACKET4035_3_R_BOLT_X; BRACKET4035_3_R_BOLT_Y; BRACKET4035_4_L_BOLT_X; BRACKET4035_4_L_BOLT_Y; BRACKET4035_4_R_BOLT_X; BRACKET4035_4_R_BOLT_Y
F02 | M8 x 20 socket cap screw | ^A[1-3]_ADAPTER_TO_PROFILE_M8x20_[12]$ | 6 | 6 | 1 | NO | 6 | 6 | 6 | PASS | A1_ADAPTER_TO_PROFILE_M8x20_1; A1_ADAPTER_TO_PROFILE_M8x20_2; A2_ADAPTER_TO_PROFILE_M8x20_1; A2_ADAPTER_TO_PROFILE_M8x20_2; A3_ADAPTER_TO_PROFILE_M8x20_1; A3_ADAPTER_TO_PROFILE_M8x20_2
F03 | M6 x 15 socket cap screw | ^DCB3025_[1-4]_[LR]_BOLT_[XY]$ ¦ ^A[1-3]_UPPER_CLEVIS_TO_PROFILE_M6x15_[12]$ | 22 | 22 | 1 | NO | 22 | 22 | 22 | PASS | A1_UPPER_CLEVIS_TO_PROFILE_M6x15_1; A1_UPPER_CLEVIS_TO_PROFILE_M6x15_2; A2_UPPER_CLEVIS_TO_PROFILE_M6x15_1; A2_UPPER_CLEVIS_TO_PROFILE_M6x15_2; A3_UPPER_CLEVIS_TO_PROFILE_M6x15_1; A3_UPPER_CLEVIS_TO_PROFILE_M6x15_2; DCB3025_1_L_BOLT_X; DCB3025_1_L_BOLT_Y; DCB3025_1_R_BOLT_X; DCB3025_1_R_BOLT_Y; DCB3025_2_L_BOLT_X; DCB3025_2_L_BOLT_Y; DCB3025_2_R_BOLT_X; DCB3025_2_R_BOLT_Y; DCB3025_3_L_BOLT_X; DCB3025_3_L_BOLT_Y; DCB3025_3_R_BOLT_X; DCB3025_3_R_BOLT_Y; DCB3025_4_L_BOLT_X; DCB3025_4_L_BOLT_Y; DCB3025_4_R_BOLT_X; DCB3025_4_R_BOLT_Y
F04 | SP408 M8 spring slot nut | ^BRACKET4035_[1-4]_[LR]_BOLT_[XY]$ ¦ ^A[1-3]_ADAPTER_TO_PROFILE_M8x20_[12]$ | 22 | 22 | 1 | YES | 22 | 22 | 22 | PASS | A1_ADAPTER_TO_PROFILE_M8x20_1; A1_ADAPTER_TO_PROFILE_M8x20_2; A2_ADAPTER_TO_PROFILE_M8x20_1; A2_ADAPTER_TO_PROFILE_M8x20_2; A3_ADAPTER_TO_PROFILE_M8x20_1; A3_ADAPTER_TO_PROFILE_M8x20_2; BRACKET4035_1_L_BOLT_X; BRACKET4035_1_L_BOLT_Y; BRACKET4035_1_R_BOLT_X; BRACKET4035_1_R_BOLT_Y; BRACKET4035_2_L_BOLT_X; BRACKET4035_2_L_BOLT_Y; BRACKET4035_2_R_BOLT_X; BRACKET4035_2_R_BOLT_Y; BRACKET4035_3_L_BOLT_X; BRACKET4035_3_L_BOLT_Y; BRACKET4035_3_R_BOLT_X; BRACKET4035_3_R_BOLT_Y; BRACKET4035_4_L_BOLT_X; BRACKET4035_4_L_BOLT_Y; BRACKET4035_4_R_BOLT_X; BRACKET4035_4_R_BOLT_Y
F05 | SP306 M6 spring slot nut | ^DCB3025_[1-4]_[LR]_BOLT_[XY]$ ¦ ^A[1-3]_UPPER_CLEVIS_TO_PROFILE_M6x15_[12]$ | 22 | 22 | 1 | YES | 22 | 22 | 22 | PASS | A1_UPPER_CLEVIS_TO_PROFILE_M6x15_1; A1_UPPER_CLEVIS_TO_PROFILE_M6x15_2; A2_UPPER_CLEVIS_TO_PROFILE_M6x15_1; A2_UPPER_CLEVIS_TO_PROFILE_M6x15_2; A3_UPPER_CLEVIS_TO_PROFILE_M6x15_1; A3_UPPER_CLEVIS_TO_PROFILE_M6x15_2; DCB3025_1_L_BOLT_X; DCB3025_1_L_BOLT_Y; DCB3025_1_R_BOLT_X; DCB3025_1_R_BOLT_Y; DCB3025_2_L_BOLT_X; DCB3025_2_L_BOLT_Y; DCB3025_2_R_BOLT_X; DCB3025_2_R_BOLT_Y; DCB3025_3_L_BOLT_X; DCB3025_3_L_BOLT_Y; DCB3025_3_R_BOLT_X; DCB3025_3_R_BOLT_Y; DCB3025_4_L_BOLT_X; DCB3025_4_L_BOLT_Y; DCB3025_4_R_BOLT_X; DCB3025_4_R_BOLT_Y
F06 | M10 x 1.5 threaded rod, 285 mm | ^A[1-3]_M10x1p5_FINE_STUD_L53$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_M10x1p5_FINE_STUD_L53; A2_M10x1p5_FINE_STUD_L53; A3_M10x1p5_FINE_STUD_L53
F07 | DIN 439 M10 thin jam nut | ^A[1-3]_2x_M10_DIN439_THIN_JAM_NUTS$ | 6 | 3 | 2 | NO | 3 | 3 | 3 | PASS | A1_2x_M10_DIN439_THIN_JAM_NUTS; A2_2x_M10_DIN439_THIN_JAM_NUTS; A3_2x_M10_DIN439_THIN_JAM_NUTS
F08 | Lower shoulder pin and prevailing-torque locknut set | ^A[1-3]_LOWER_M8_SHOULDER_BOLT_GRIP46$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_LOWER_M8_SHOULDER_BOLT_GRIP46; A2_LOWER_M8_SHOULDER_BOLT_GRIP46; A3_LOWER_M8_SHOULDER_BOLT_GRIP46
F09 | Upper shoulder pin and prevailing-torque locknut set | ^A[1-3]_UPPER_M10_SHOULDER_BOLT_GRIP32$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_UPPER_M10_SHOULDER_BOLT_GRIP32; A2_UPPER_M10_SHOULDER_BOLT_GRIP32; A3_UPPER_M10_SHOULDER_BOLT_GRIP32
F10 | Upper side shim | ^A[1-3]_UPPER_ID10_OD18_SHIM_3MM_[12]$ | 6 | 6 | 1 | NO | 6 | 6 | 6 | PASS | A1_UPPER_ID10_OD18_SHIM_3MM_1; A1_UPPER_ID10_OD18_SHIM_3MM_2; A2_UPPER_ID10_OD18_SHIM_3MM_1; A2_UPPER_ID10_OD18_SHIM_3MM_2; A3_UPPER_ID10_OD18_SHIM_3MM_1; A3_UPPER_ID10_OD18_SHIM_3MM_2
F11 | M4 x 40 socket cap screw plus M4 nyloc nut | ^A[1-3]_PLUG_RETAINER_M4_GRIP32$ | 3 | 3 | 1 | NO | 3 | 3 | 3 | PASS | A1_PLUG_RETAINER_M4_GRIP32; A2_PLUG_RETAINER_M4_GRIP32; A3_PLUG_RETAINER_M4_GRIP32
F12 | LOCTITE 243 medium-strength threadlocker |  | 1 | 0 | 1 | YES | 0 | 0 | 0 | PASS

## Custom Parts
Custom Machining and Special Hardware Quote List
Use with fabrication/manual_rev_m1_custom_part_spec_2026-09-02.md and the native F3D/STEP. Quote one A1 trial set before releasing the full quantity.
Line | Item | Exact specification | Material | Used | Order | Unit | Budget unit | Budget extended | Status | Quote/inspection condition
C01 | Lower local adapter | 120 x 80 x 8; two diameter-9 through holes at 96 pitch; two M8 x 1.25 tapped holes at 40 pitch | A6061-T6 | 3 | 3 | EA | 30000 | 90000 | READY_TO_QUOTE | Tap after diameter-6.8 drilling; deburr all edges
C02 | Lower one-piece clevis | Base 60 x 50 x 8; clear gap 34; ears t6; outside width 46; pivot diameter 8.2; pivot center 28 above base top | A6061-T6 | 3 | 3 | EA | 120000 | 360000 | READY_TO_QUOTE | Machine from one billet; no welding; maintain coaxial pivot bores
C03 | Upper one-piece clevis | Base 100 x 60 x 8; mounting pitch 84; clear gap 20; ears t6; outside width 32; pivot diameter 10.2 | A6061-T6 | 3 | 3 | EA | 120000 | 360000 | READY_TO_QUOTE | Machine from one billet; no welding; maintain coaxial pivot bores
C04 | Finished outer tube | OD32 x ID28 x L160; upper 21 mm housing reamed to diameter 28.000-28.021; lower pivot bore diameter8.2; coarse-pin bore diameter8 +0.1/0 | Aluminum tube, 6061-T6 preferred | 3 | 4 | EA | 50000 | 200000 | READY_TO_QUOTE | Machine bushing housing after tube receipt; inspect ID before reaming
C05 | Finished inner tube | OD25 shaft tolerance 24.948-25.000 x ID21 x L150; six diameter8 +0.1/0 coarse holes at 15 pitch; one diameter-4.2 retainer hole | Aluminum tube, 6061-T6 preferred | 3 | 4 | EA | 35000 | 140000 | READY_TO_QUOTE | Verify actual OD is within 24.948-25.000 before ordering batch machining
C06 | Lower guide ring | OD27.6 x ID25.10 x L12, split installation permitted | POM-C | 3 | 4 | EA | 15000 | 60000 | READY_TO_QUOTE | Deburr and dry-fit with actual inner/outer tubes
C07 | M10 threaded insert plug | OD20.8 x L30; axial M10 x 1.5 thread depth 22 minimum; diameter-4.2 retainer cross hole 7.5 from plug lower end (22.5 from outer end) | A6061-T6 | 3 | 4 | EA | 25000 | 100000 | READY_TO_QUOTE | Cross drill plug and inner tube together after dry fit
F08 | Lower shoulder pin and prevailing-torque locknut set | Shoulder diameter 7.98 h9, grip 46, head diameter14 x 7; M8 threaded end and 13 AF x 6.5 locknut | SCM435, hardened and black oxide | 3 | 4 | SET | 30000 | 120000 | READY_TO_QUOTE | No thread may lie inside either clevis ear or outer tube pivot bore
F09 | Upper shoulder pin and prevailing-torque locknut set | Shoulder diameter 9.98 h9, grip 32, head diameter16 x 5; M10 threaded end and 17 AF x 8 locknut | SCM435, hardened and black oxide | 3 | 4 | SET | 35000 | 140000 | READY_TO_QUOTE | No thread may lie inside clevis ears, shims, or PHS10 bore
F10 | Upper side shim | ID10.2, OD18, thickness3 | SUS304 | 6 | 8 | EA | 5000 | 40000 | READY_TO_QUOTE | Thickness tolerance +/-0.05 preferred; verify free articulation after assembly

## Verification
Assembly, Interference, Section and BOM Verification Record
Corrected design was verified, then the complete process was repeated once without source changes. All values below are traceable to JSON audit files in the output folder.
Round | Check | Pass | Items checked | Issues | Result | Evidence | Detail
Round 1 | Fusion interference | 1 | 129 | 0 | PASS | Design.analyzeInterference | Coincident faces excluded
Round 1 | Fusion interference | 2 | 129 | 0 | PASS | Design.analyzeInterference | Coincident faces excluded
Round 1 | Fusion interference | 3 | 129 | 0 | PASS | Design.analyzeInterference | Coincident faces excluded
Round 1 | Fusion section | 1 | 1 | 0 | PASS | Manual_3RPS_RevM1_A1_SECTION_PASS_1.png | X offset 0 mm
Round 1 | Fusion section | 2 | 1 | 0 | PASS | Manual_3RPS_RevM1_A1_SECTION_PASS_2.png | X offset 3 mm
Round 1 | Fusion section | 3 | 1 | 0 | PASS | Manual_3RPS_RevM1_A1_SECTION_PASS_3.png | X offset -3 mm
Round 1 | Independent STEP | 1 | 253 | 0 | PASS | 36 cross-group + 9 self-group reports | 700 x 700 x 300 mm
Round 1 | BOM-CAD mapping | 1 | 129 | 0 | PASS | 28 BOM rows / 129 native components | 129 covered
Round 1 | BOM-CAD mapping | 2 | 129 | 0 | PASS | 28 BOM rows / 129 native components | 129 covered
Round 1 | BOM-CAD mapping | 3 | 129 | 0 | PASS | 28 BOM rows / 129 native components | 129 covered
Round 2 | Fusion interference | 1 | 129 | 0 | PASS | Design.analyzeInterference | Coincident faces excluded
Round 2 | Fusion interference | 2 | 129 | 0 | PASS | Design.analyzeInterference | Coincident faces excluded
Round 2 | Fusion interference | 3 | 129 | 0 | PASS | Design.analyzeInterference | Coincident faces excluded
Round 2 | Fusion section | 1 | 1 | 0 | PASS | Manual_3RPS_RevM1_A1_SECTION_PASS_1.png | X offset 0 mm
Round 2 | Fusion section | 2 | 1 | 0 | PASS | Manual_3RPS_RevM1_A1_SECTION_PASS_2.png | X offset 3 mm
Round 2 | Fusion section | 3 | 1 | 0 | PASS | Manual_3RPS_RevM1_A1_SECTION_PASS_3.png | X offset -3 mm
Round 2 | Independent STEP | 1 | 253 | 0 | PASS | 36 cross-group + 9 self-group reports | 700 x 700 x 300 mm
Round 2 | BOM-CAD mapping | 1 | 129 | 0 | PASS | 28 BOM rows / 129 native components | 129 covered
Round 2 | BOM-CAD mapping | 2 | 129 | 0 | PASS | 28 BOM rows / 129 native components | 129 covered
Round 2 | BOM-CAD mapping | 3 | 129 | 0 | PASS | 28 BOM rows / 129 native components | 129 covered
Engineering metrics
Workspace poses | 27 | count | 27-point Z/pitch/roll sweep
Required pin length min | 219.1426 | mm | Workspace solver
Required pin length max | 279.6423 | mm | Workspace solver
Manual pin range | 213..303 | mm | Six coarse holes plus fine thread
Max constraint residual | 6.537e-13 | mm | Nonlinear 3-RPS closure
Coarse-hole diameter max | 8.1 | mm | IMAO diameter8 +0.1/0
Collapsed envelope | 700 x 700 x 300 | mm | Independent STEP bounds

## Sources
Dimension and Procurement Source Register
Technical dimensions use official catalogs or saved product detail images. Retail prices and availability must be reconfirmed at checkout or quotation.
Part/source | Source type | Saved evidence | Used for | Role | URL
THK PHS10 | Official catalog PDF | web_research/evidence/2026-09-01/manual_rev_m1/THK_PHS_catalog_en_a23_006.pdf | Bore, OD, width, thread, capacity, articulation | TECHNICAL BASIS | https://www.thk.com/
IMAO BJ775-08040-SUS | Official product PDF/CAD listing | web_research/evidence/2026-09-01/manual_rev_m1/IMAO_BJ775_SUS.pdf | Pin diameter, grip, hole tolerance, material | TECHNICAL BASIS | https://www.imao.com/catalog/en/categoryviews/?category=%24900337&categorycode=%24WHSSAP%2C%24whs&page=1
igus JFM-2528-21 | Official catalog PDF | web_research/evidence/2026-09-01/manual_rev_m1/IGUS_JFM_catalog.pdf | Bearing and housing/shaft tolerances | TECHNICAL BASIS | https://www.igus.com/
DNF4040 / DNF3030 | NAVIMRO saved detail images | web_research/evidence/2026-08-31/ | Profile envelope, slots, center bores | TECHNICAL + BUY | https://www.navimro.com/
4035 / DCB3025 | NAVIMRO saved detail images | web_research/evidence/2026-08-31/ | Bracket envelopes and holes/slots | TECHNICAL + BUY | https://www.navimro.com/
JFM-2528-21 price | DeviceMart product page | Product 10896543 | VAT-included price and lead-time note | BUY | https://www.devicemart.co.kr/goods/view?no=10896543
PHS10 price | SL System product category | PHS10 RH | Indexed retail price | BUY | https://myslmall.com/category/PHS/146/
NAVIMRO items | 2026-09-01 candidate BOM | procurement/profile_radial_revd_navimro_candidate_bom_2026-09-01.csv | Codes and VAT-included screen prices | BUY | https://www.navimro.com/